## alpha-1.0.0
US number | LE | Function Point | Description | Details | Risk | Status | Task | Time Line | Dependency | Children | spare
K_1 | N/A | Main function | As a designer, i want KITT own a GUI for interaction, also could be setting for opening, close, preference setting. | N/A | N/A | N/A |  | 4/21/2013 | N/A | K_3 K_4 K_5 K_2
K_2 | N/A | Handle input | As a designer, i want KITT could handle input resource ( TTCN code, parameter file setting,etc.). | design US K_2_X | N/A | N/A |  | 4/21/2014 | N/A | k_2_1; k_2_2; k_2_3
K_3 | N/A | handle basic level output | As a designer, i want KITT could do outputting. Generating resources, marker, warning, error, message sequence diagram, comments etc. Which based on input(Builder funalities). | N/A | N/A | N/A |  | 4/21/2015 | N/A
K_4 | N/A | handle high level output | As a designer, i want KITT could be a compiler, ownning syntax checking, compilation, running functionalities. (Builder funalities). | N/A | N/A | N/A |  | 4/21/2016 | N/A
K_5 | N/A | Configuration | As a designer, I want KITT could to be configuratting and setting |  | N/A | N/A |  | 4/21/2013 | N/A
K_2_1 | 1 | Project navigation tree | As a programmer I will implement project navigation tree for KITT project. | 1.create navigation view | Not sure how many root nodes are needed;currently, default project structure like maven project: >>src >>bin >>resources |  |  |  | N/A
K_2_2 | 1 | Project creating wizard | As a programmer I will implement project creating wizard for KITT |  | Not sure how many parameter should setting before creating a project; currently, only project name is needed |  |  |  | N/A
K_2_3 | 2 | Project operation | As a programmer I will implement deleting; importing; exporting function for KITT project
K_2_4 | 1 | TTCN editor creating | As a programmer I will implement a TTCN editor
K_2_5 | ? | KITT project | As a programmer I will implement Kitt project navigatior. | 1.create KITT navigation view | 4. currently implementing show tree functions. Promote logger and other utils. 3.how to get current project and initialize its navigator 1.Not sure which properties needed for this project object 2. is there a Project object new to create? | Done | 1.create view class | 4/28/2013 : blocked to wait US_K_2_6 4/22/2013:projectnavigationview is ongoing with Model and providers.Content provider and Label provider implemented, task to KittProjectNavigatorView.init() line 70 4/21/2013 : start to implement | US_K_2_6 | US_K_2_6
K_2_5 | 2 | KITT project | As a programmer I will implement Kitt project navigatior. | 2.create KITT navigation view | 3.how to get current project and initialize its navigator 1.Not sure which properties needed for this project object 3. is there a Project object new to create? | done | 1.create content provider;label provider | 4/23/2013:implement content provider,label provider.
K_2_6 | 3 | Navigator | As a programer I will implement the context menu for navigator | create context menu | 1.Not sure current context menu works fine for evaluating selection. | Done | 1. create context menu | 4/28/2013 : implementing context menu for navigator |  | US_K_2_7 k_2_10
K_2_8 | 3 | Navigator | As a programer I will implement the context menu for navigator | Create tree view | 1.how to handle files than kitt related file | done | 1.create tree view | 5/2/2013 : implementing tree view. |  | us_k_2_9 us_k_2_10
K_2_9 | 1 | Navigator | As a programmer I will implement basic tree node operation, so that other works and go on. | create tree node contrller |  | done | 1.create basic tree operation | 5/5/2013 : done with unit test. 5/4/2013: implementing tree controller : add node, delete node;//TODO is modify node. 5/4/2013: implementing tree controller
K_2_10 | 2 | Navigator | As a programmer I will implement tree node operation listener, so that also tree operation can be call back to view | 1.implementing fresh callback listener |  | Done |  | 5/5/2013 : implementing fresh call back functionality
k_2_11 | 4 | Navigator | As a programmer I will implement actions for context menu | create refresh action | some bug while import trhandler, need feature investigation. | Done |  | 6/8/2013 : view level fresh complete, waiting for persistence level refresh. 6/6/2013 : new action is partial done, with default new wizards. Need to implement kitt specific new wizard
K_2_13 | 3 | Navigator | As a programer I will implement low level resource handling so that resource could create properly while view changed | Resource create handling | 6.30 : fixed fault that can't delete tree node view from view point of view, use Iresource full path as hash key of tree node map; still need to fix that kitt can't detect fill exsiting. 6.27 : 1.can't detect exsiting file when creating !!! 2. find a bug, will create file with same name twice by "new TTCN file" action. The file can't be delete anymore, this maybe cause by TreeNode equal method, root cause is related to creating without exsiting checking. get selection while selection change event come | Done |  | 6/17/2013 : low level file create implemented. 6/16/2013 : low level resorce handling is going
K_2_14 | 3 | Resources | As a programer I will implement resources handling | Resource delete handling |  | implemented |  | 6/23/2013 : low level resources deleting implemented.
k_2_15 | 3 | Navigator | As a programmer I will implement double click handling on navigator tree | create double click handler | 7.9 : fixed. 6.27 : 1.can't detect exsiting file when creating !!! 2. find a bug, will create file with same name twice by "new TTCN file" action. The file can't be delete anymore, this maybe cause by TreeNode equal method, root cause is related to creating without exsiting checking. | Done
K_2_4_1 | 1 | TTCN editor creating | As a programmer I will implement ttcn editor. | 1.create editor template 2. improve open with action | 7.29 fixed this risk 7.1 still missing open with other editor functionality | block, maybe ttcn navigator will be replace by CNF later |  | 7/1/2013 : editor template created; openwithother action improved.
K_2_4_2 |  | TTCN editor creating | As a programmer I will implement IDocumentationProvider to mapping resources input to Idocument. |  |  | Done |  | 7.29 customized DocumentationProvider not needed currently.
K_2_4_3 |  | ttcn editor creating | As a programmer I will implement BasicDocumentScanner which could scan whole documentation(for basic document partition while document setup) |  |  | DONE |  | [[[7.29 TTCNDocumentPartitionScanner is under implementing. 8.1 Defined basic partitions and rules, implement basci partition scanner. Add scanner tester. 7.31 analysed the process of input change. Still need to analyse how does scanner work. 1.add new contentType, currently its usage is still not very clear.]]]] 8.29 : while there are a range needs to be partitioning, the scanner always scans from the first offset, if the token does begin from the first offset, how can it be proccessed.???!!!! 9.2 : previous problem has been solved, reference to EverNot Eclipse>>scanner. Currently, problem is those SemanticBlockPartition can't be category to __content_type_position.
K_2_4_4 |  | TTcn editor creating | As a programmer I will implement TTCN document scanners, so that Position calculation, coloring and so on could implemented based them. |  |  | DONE |  | 9.6 : Based on JavaScanner implementing strategy, I'm implementing TTCNCodeScanner current. Currenly, Keyword , operator and bracket rules has been completed basicly.
K_2_4_15 |  | ttcn editor creating | As a programmer I will implement ttcnsourceviewerconfiguration, so that all ttcn syntax could be highlight. |  |  | DONE |  | 9.10 : assemble kinds of scanners into TTCNEditor and TTCNSourceViewerConfiguration, reference to JavaEditorSourceViewerConfiguration. 10.13 : basic syntax high light works fine (keyword, operator, bracket). Next step is add more high light unit into editor. E.g. module, function, test case, control part and so on. 1017 . Bug found, the keywords will be highlight even they are part of one other word. Because I thing it is due to the rule doesn't define the right keyword starting. Ask from stack over flow for help. 10.27 basicly, all keyword highlight complete
K_2_4_17 | 1 | TTCN editor action | As a designer I want TTCN editor content can highlight content dynamically based on user's selection | Abstract user story, It will be implemented by k_2_4_17_x US.
K_2_4_17_1 | 2 | TTCN editor action | As a programmer I will implement occurrence highlight dynamically based on user's selection | 12.4 Line-based indexing draft completed, so that words could be indexed and it could be used by occurrence highlight later. 12.17 Occurrence highlight implemented. | 12.4 debugging is ongoging. 12.9 Highlight is working now, but overview ruler doesn't work. Continue debugging. 12.17 There is problems with cleaning highlight before document and cursor position changing. | Done
K_2_4_17_2 | 1 | TTCN editor action | As a programmer I will implement TTCN field open declaring based on highlight |  | 12.4 debugging is ongoging. 12.9 Highlight is working now, but overview ruler doesn't work. Continue debugging.
K_2_4_18 |  | TTCN editor action | AS a designer I want TTCN editor can format code. | Abstract user story. Investigating. |  | Not start
K_2_4_18_1 |  | TTCN editor action | As a programmer I will implement TTCN code format. |  |  | Not start
K_2_4_18_2 |  | TTCN editor action | As a programmer I will implement formatter configuration, so that format rule could be defined. |  |  | Not start
k_2_4_19 | 1 | TTCN outliner | As designer I want ttcn editor could have a outliner, so that every code union could be outlining and selected. | Abstract design |  | Planed
k_2_4_19_1 | 2014-02-16 | TTCN outliner | As programmer I will implement code union structure, so that outline could use it. | 11.3 Implementing outline tree viewer, trying to implement selection highlight. | 11.3 Issues: 1)Seems outline doesn't load while open editor, need to click editor one time. 2) highlight strategy is not very good.E.g.: how to reset highlight after selection. Need to check how does java outline does highlight. 3) have no idea with how to link to editor while select element on outline. | Implementing |  | 2014.3.7 : Basic outline elements are ready! 2014.3.4 : Miss some of Outline element ,outline content provider needs improvement, complete all basic outline element (testcase, function, template, type def, const def)
K_2_4_6 |  |  | as a programmer I will implement TTCN global ruler |  | 10.29 still not clear with Annotation model and rulers. | block
K_2_4_8 | 1 | TTCN editor creating | As a programmer I will implement TTCNAnnotationModel | (1)annotation model setup (2)annotation model update | 8.8 (1)annotation model setup by DocumentPrivder#createFileInfo (2) annotation updating is unclear!!! | block |  | 8.8 IAnnotationFactory implementted by DocumentProvider; AnnotationModel implementing is ongoing.
k_2_4_9 | low | Additional function | As a designer I want KITT could do TTCN searcher which like JDT does. E.g. open type, ttcn searcher
K_2_5_1 | ? | TTCN core | As a desiginer I want KITT to introduce a conception "module path" which likes "CLASSPATH", so resources could reference to each other based on the conception | Implementing TTCNElement referencing and indexing machenism. | 2014.1.19 : Paring IFIle to ttcn element is waiting to implement. 2014.1.13 : (a) .Unclear with how to get Idocument from Ifile;(b). Parsing Ifile to ttcn element. 2014.1.5 : Resources change event is not familiar, needs to check weather right resource change event could be handled by TTCNResourceListener. | DONE |  | 2014.3.4 : basicly, traverse folders and collect ".ttcn" file 2014.1.19 : Implementing CoreIndex, initializing project, package, module etc. 2014.1.13 : setup a basic type indexing framewok. Need to debug. 2014.1.10 : adding color for string constants 2014.1.6 : PostChangeVisitor's logic should change, handle different delta.getKind() seperately. 2014.1.5 : implementing resource-element mapping mechanism Include Core index, Core etc.
K_2_5_2 | 2014-02-12 | TTCN core | As a designer I want KITT has a TTCN parser. | Goal : 1. Create a parser based on Antlr4 2. Create CompilationUnit element | 2014.2.11 : basic function def is not a good one. need to check! | Implementing |  | 2014.3.4 : compilation unit parse complete, but there is bugs. Anyway, i can put this task into done, and start a BUG task. 2014.2.21 : basicly, parser has been completed, reset thing is to design a way which connects correct core index with parser in a good way 2014.2.11 : TTCN basic function def, altstep def, template def completed. 2014.2.10 : TTCN basic literal and TLD has been defined by ANTLR4. AP;(1)try to verify it as many as possible (by stript);(2) start to implement basic parsing listener logic
K_2_5_3 | 2014-02-13 | TTCN Core | As a grogrammer i will implement TTCN parser listener, so that syntax strcuture can be generated |  |  | DONE |  | 2014.3.4 : compilation unit level basic listener has been completed.
K_2_5_4 | 2014-02-15 | TTCN Core | As a programmer i will implement TTCN core syntax indexing, so that sources can reference to each other. |  |  | DONE |  | 2014.3.4 : Compilation unit indexing has been completed.

## alpha-1.0.1
KITT 1.0.1 backlog
Release description | 1.0.0 mainly focus on syntax complement
US ID | Description | Comment | Assignee | LE
1.0.1_1 | As a programmer I will implement module parameter definition parsing. |  | Yuding Zhou
1.0.1_2 | As a programmer I will implement attribute definition parsing. |  | Yuding Zhou
1.0.1_3 | As a programmer I will implement group definition parsing | 2014/3/18:Done | Yuding Zhou